## Meridian Gantt Chart
Meridian Spatial Cartographer
UCS503P: Software Engineering (TIET) - Milestone Project Schedule
Project Lead: Rahul Dadwal |  | Project Start: 8/5/2026 | Current Timeline: 10/27/2026 | Milestone: Week 11 Active
TASK | ASSIGNED TO | PROGRESS | START | END | Aug 03, 2026 | [6 empty] | Aug 10, 2026 | [6 empty] | Aug 17, 2026 | [6 empty] | Aug 24, 2026 | [6 empty] | Aug 31, 2026 | [6 empty] | Sep 07, 2026 | [6 empty] | Sep 14, 2026 | [6 empty] | Sep 21, 2026 | [6 empty] | Sep 28, 2026 | [6 empty] | Oct 05, 2026 | [6 empty] | Oct 12, 2026 | [6 empty] | Oct 19, 2026 | [6 empty] | Oct 26, 2026
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1: Team Formation & Problem Identification
Team Formation & Project Brainstorming | Team (All Members) | 100% | 8/5/26 | 8/7/26 | bar: Aug 03, 2026 W to Aug 03, 2026 F
Real-World Problem Analysis & Exploration | Rahul Dadwal | 100% | 8/6/26 | 8/9/26 | bar: Aug 03, 2026 T to Aug 03, 2026 S
Meridian Latent Cartographer Concept Study | Jyotsna Sachdeva | 100% | 8/7/26 | 8/10/26 | bar: Aug 03, 2026 F to Aug 10, 2026 M
Project Motivation & Problem Domain Exploration | Bisman Singh Rai | 100% | 8/8/26 | 8/11/26 | bar: Aug 03, 2026 S to Aug 10, 2026 T
Problem Statement & Direction Finalization | Team (All Members) | 100% | 8/10/26 | 8/11/26 | bar: Aug 10, 2026 M to Aug 10, 2026 T
Phase 2: Project Proposal & Requirements Analysis
Proposal Development & Solution Documentation | Jyotsna Sachdeva | 100% | 8/12/26 | 8/15/26 | bar: Aug 10, 2026 W to Aug 10, 2026 S
Functional Analysis & User Interaction Study | Rahul Dadwal | 100% | 8/13/26 | 8/16/26 | bar: Aug 10, 2026 T to Aug 10, 2026 S
Data Flow Analysis & Workflow Mapping | Jyotsna Sachdeva | 100% | 8/14/26 | 8/17/26 | bar: Aug 10, 2026 F to Aug 17, 2026 M
Presentation Information Gathering & Structure | Bisman Singh Rai | 100% | 8/12/26 | 8/16/26 | bar: Aug 10, 2026 W to Aug 10, 2026 S
Presentation Content Drafting (Problem & Goals) | Bisman Singh Rai | 100% | 8/15/26 | 8/18/26 | bar: Aug 10, 2026 S to Aug 17, 2026 T
Phase 3: Architectural Modeling & Initial Diagrams
Initial Use Case Diagram & Actor Analysis | Rahul Dadwal | 100% | 8/19/26 | 8/22/26 | bar: Aug 17, 2026 W to Aug 17, 2026 S
Level 0 Context DFD Preparation | Jyotsna Sachdeva | 100% | 8/19/26 | 8/22/26 | bar: Aug 17, 2026 W to Aug 17, 2026 S
Level 1 DFD Process & Data Flow Modeling | Jyotsna Sachdeva | 100% | 8/21/26 | 8/25/26 | bar: Aug 17, 2026 F to Aug 24, 2026 T
Level 2 DFD Internal Workflow Modeling | Rahul Dadwal | 100% | 8/22/26 | 8/25/26 | bar: Aug 17, 2026 S to Aug 24, 2026 T
Project Presentation Slide Deck Complete Draft | Bisman Singh Rai | 100% | 8/19/26 | 8/25/26 | bar: Aug 17, 2026 W to Aug 24, 2026 T
Phase 4: Detailed Design & Refinement
Detailed Use Case Diagram & Interaction Extension | Rahul Dadwal | 100% | 8/26/26 | 8/29/26 | bar: Aug 24, 2026 W to Aug 24, 2026 S
Detailed Level 0 & Level 1 DFD Refinement | Jyotsna Sachdeva | 100% | 8/26/26 | 8/30/26 | bar: Aug 24, 2026 W to Aug 24, 2026 S
Detailed Level 2 DFD Expansion & Cross-Sync | Rahul Dadwal | 100% | 8/28/26 | 9/1/26 | bar: Aug 24, 2026 F to Aug 31, 2026 T
Presentation Updates for New Project Scope | Bisman Singh Rai | 100% | 8/26/26 | 8/30/26 | bar: Aug 24, 2026 W to Aug 24, 2026 S
Final Presentation Polish & Submission Readiness | Bisman Singh Rai | 100% | 8/30/26 | 9/1/26 | bar: Aug 24, 2026 S to Aug 31, 2026 T
Phase 5: Foundation Prototype – Milestone 1 (Level 0 Implementation)
Manifest V3 Extension Setup & Local Runtime Architecture | Rahul Dadwal | 100% | 9/2/26 | 9/5/26 | bar: Aug 31, 2026 W to Aug 31, 2026 S
Transformers.js & MiniLM WASM Worker Pipeline Setup | Rahul Dadwal | 100% | 9/3/26 | 9/7/26 | bar: Aug 31, 2026 T to Sep 07, 2026 M
Data Contracts & Worker IPC Message Protocol | Jyotsna Sachdeva | 100% | 9/4/26 | 9/7/26 | bar: Aug 31, 2026 F to Sep 07, 2026 M
Offline Inference Verification & Similarity Testing | Jyotsna Sachdeva | 100% | 9/5/26 | 9/8/26 | bar: Aug 31, 2026 S to Sep 07, 2026 T
Demonstration Planning & Overview Review | Bisman Singh Rai | 100% | 9/5/26 | 9/8/26 | bar: Aug 31, 2026 S to Sep 07, 2026 T
Phase 6: Activity Diagrams, Architecture Implementation & Prototype Report
Activity Diagram & Swimlane Workflow Modeling | Rahul Dadwal | 100% | 9/9/26 | 9/12/26 | bar: Sep 07, 2026 W to Sep 07, 2026 S
Worker Pipeline Optimization & Memory Management | Rahul Dadwal | 90% | 9/10/26 | 9/15/26 | bar: Sep 07, 2026 T to Sep 14, 2026 T
Prototype Stage Report (Technical Architecture & Benchmarks) | Rahul Dadwal | 95% | 9/12/26 | 9/15/26 | bar: Sep 07, 2026 S to Sep 14, 2026 T
Entity-Relationship (ER) Storage Schema Modeling | Jyotsna Sachdeva | 100% | 9/9/26 | 9/12/26 | bar: Sep 07, 2026 W to Sep 07, 2026 S
Offline Latency Profiling & Multi-Sentence Validation | Jyotsna Sachdeva | 90% | 9/11/26 | 9/14/26 | bar: Sep 07, 2026 F to Sep 14, 2026 M
Prototype Presentation Technical Architecture Slides | Jyotsna Sachdeva | 95% | 9/12/26 | 9/15/26 | bar: Sep 07, 2026 S to Sep 14, 2026 T
Presentation Assembly & Slide Formatting | Bisman Singh Rai | 95% | 9/13/26 | 9/15/26 | bar: Sep 07, 2026 S to Sep 14, 2026 T
Phase 7: Mid-Semester Evaluation & Prototype Defense
Live Prototype Demonstration & WASM Execution Defense | Rahul Dadwal | 95% | 9/16/26 | 9/20/26 | bar: Sep 14, 2026 W to Sep 14, 2026 S
Architecture Modeling & DFD/ER Data Flow Defense | Jyotsna Sachdeva | 95% | 9/16/26 | 9/20/26 | bar: Sep 14, 2026 W to Sep 14, 2026 S
Evaluation Presentation Delivery & Session Coordination | Bisman Singh Rai | 100% | 9/16/26 | 9/21/26 | bar: Sep 14, 2026 W to Sep 21, 2026 M
Evaluator Question Logging & Feedback Synthesis | Team (All Members) | 90% | 9/19/26 | 9/22/26 | bar: Sep 14, 2026 S to Sep 21, 2026 T
Phase 8: Mid-Semester Examination Period
Mid-Semester Theory & Practical Examinations | Team (All Members) | 100% | 9/23/26 | 10/4/26 | bar: Sep 21, 2026 W to Sep 28, 2026 S
Technical Architecture Retrospective & Milestone 2 Scope | Rahul Dadwal | 85% | 10/4/26 | 10/7/26 | bar: Sep 28, 2026 S to Oct 05, 2026 W
IndexedDB Scalability & Storage Requirements Review | Jyotsna Sachdeva | 80% | 10/4/26 | 10/7/26 | bar: Sep 28, 2026 S to Oct 05, 2026 W
Presentation Assets Organization & Archive Management | Bisman Singh Rai | 90% | 10/4/26 | 10/7/26 | bar: Sep 28, 2026 S to Oct 05, 2026 W
Phase 9: Ingestion, Storage & Workflow Architecture Planning
Readability DOM Parsing & Extension Extraction Research | Rahul Dadwal | 85% | 10/7/26 | 10/10/26 | bar: Oct 05, 2026 W to Oct 05, 2026 S
Background Service Worker IPC State Machine Design | Rahul Dadwal | 80% | 10/9/26 | 10/12/26 | bar: Oct 05, 2026 F to Oct 12, 2026 M
Sliding-Window Tokenizer (256w/50o) Algorithm Formulation | Rahul Dadwal | 75% | 10/10/26 | 10/13/26 | bar: Oct 05, 2026 S to Oct 12, 2026 T
Tiered Client-Side Persistence Architecture (IndexedDB & OPFS) | Jyotsna Sachdeva | 85% | 10/7/26 | 10/11/26 | bar: Oct 05, 2026 W to Oct 05, 2026 S
Object Store Schemas & Composite Key Indexing Plan | Jyotsna Sachdeva | 80% | 10/9/26 | 10/12/26 | bar: Oct 05, 2026 F to Oct 12, 2026 M
Database Transaction Boundaries & Atomic Save Rollback Rules | Jyotsna Sachdeva | 75% | 10/11/26 | 10/13/26 | bar: Oct 05, 2026 S to Oct 12, 2026 T
Team Meeting Minutes & Sprint Schedule Alignment | Bisman Singh Rai | 95% | 10/7/26 | 10/10/26 | bar: Oct 05, 2026 W to Oct 05, 2026 S
Cognitive User Journey & Web Research Workflow Study | Bisman Singh Rai | 85% | 10/8/26 | 10/12/26 | bar: Oct 05, 2026 T to Oct 12, 2026 M
Spatial Canvas UI Design Pattern Reference Collection | Bisman Singh Rai | 90% | 10/10/26 | 10/13/26 | bar: Oct 05, 2026 S to Oct 12, 2026 T
Phase 10: Canvas Layout, Scalability & Retrieval Strategy Planning
Dynamic 2D Spatial Layout & UMAP Algorithm Research | Rahul Dadwal | 80% | 10/14/26 | 10/17/26 | bar: Oct 12, 2026 W to Oct 12, 2026 S
Non-Blocking UMAP Projection Web Worker Architecture | Rahul Dadwal | 75% | 10/16/26 | 10/19/26 | bar: Oct 12, 2026 F to Oct 19, 2026 M
HTML5 Canvas / Konva Viewport Rendering Pipeline (60 FPS) | Rahul Dadwal | 70% | 10/17/26 | 10/20/26 | bar: Oct 12, 2026 S to Oct 19, 2026 T
In-Memory Cosine Similarity & SQ8 Quantization Algorithm | Jyotsna Sachdeva | 80% | 10/14/26 | 10/18/26 | bar: Oct 12, 2026 W to Oct 12, 2026 S
Data Lifecycle Rules & 7-Day Snapshot Cache Pruning Policy | Jyotsna Sachdeva | 85% | 10/16/26 | 10/19/26 | bar: Oct 12, 2026 F to Oct 19, 2026 M
Automated Test Strategy & Edge-Case DOM Fixtures Specification | Jyotsna Sachdeva | 75% | 10/17/26 | 10/20/26 | bar: Oct 12, 2026 S to Oct 19, 2026 T
Non-Technical Usability Analysis & Tab Capture Friction | Bisman Singh Rai | 85% | 10/14/26 | 10/17/26 | bar: Oct 12, 2026 W to Oct 12, 2026 S
Card Density & Floating Toolbar Usability Review | Bisman Singh Rai | 80% | 10/16/26 | 10/19/26 | bar: Oct 12, 2026 F to Oct 19, 2026 M
Sprint Task Checklists & Journal Log Synchronization | Bisman Singh Rai | 90% | 10/18/26 | 10/20/26 | bar: Oct 12, 2026 S to Oct 19, 2026 T
Phase 11: Class & Sequence Modeling, OOP Implementation, Sequence Flow & UX Redesign
System Class Diagram Design (Core Worker & Controller Classes) | Rahul Dadwal | 90% | 10/21/26 | 10/24/26 | bar: Oct 19, 2026 W to Oct 19, 2026 S
System Sequence Diagram Modeling (End-to-End Pipeline) | Rahul Dadwal | 85% | 10/22/26 | 10/25/26 | bar: Oct 19, 2026 T to Oct 19, 2026 S
OOP Class Architecture Implementation (EmbeddingClientManager, WorkerMessageController) | Rahul Dadwal | 80% | 10/24/26 | 10/27/26 | bar: Oct 19, 2026 S to Oct 26, 2026 T
Storage Entity Class Diagram Design (DocumentRepository, StorageAdapter) | Jyotsna Sachdeva | 90% | 10/21/26 | 10/24/26 | bar: Oct 19, 2026 W to Oct 19, 2026 S
Sequence Diagram Event Orchestration & Runtime Message Flows | Jyotsna Sachdeva | 85% | 10/22/26 | 10/25/26 | bar: Oct 19, 2026 T to Oct 19, 2026 S
Asynchronous Sequence Implementation (Promise Correlation & Dispatch) | Jyotsna Sachdeva | 75% | 10/24/26 | 10/27/26 | bar: Oct 19, 2026 S to Oct 26, 2026 T
2D Research Canvas Wireframes & Ideation Redesign | Bisman Singh Rai | 85% | 10/21/26 | 10/24/26 | bar: Oct 19, 2026 W to Oct 19, 2026 S
Spatial Minimap & Floating Navigation Dock Mockups | Bisman Singh Rai | 80% | 10/23/26 | 10/26/26 | bar: Oct 19, 2026 F to Oct 26, 2026 M
Contextual Search Modal Layout & Theme Accent Specifications | Bisman Singh Rai | 85% | 10/24/26 | 10/27/26 | bar: Oct 19, 2026 S to Oct 26, 2026 T